## Three-Year SSE Plan: Wellbeing & PMC 2023 (2025-2028)

Three-year Wellbeing and Mathematics goals with milestones, responsibilities, and success indicators.

| Years | Wellbeing Focus / Targets | Mathematics Focus / Targets | Actions / Strategies | Indicators of Success |
| --- | --- | --- | --- | --- |
| 2025-2026 | Building Foundations Focus on relationships, school culture, student voice, and establishing measurement tools. | Mathematical Language & Communication Target: Improve use of mathematical vocabulary and reasoning in classes from Junior Infants to 5th. | - Conduct baseline wellbeing audit (student, staff, parent surveys) using PDST/Oide tools. - Set up Wellbeing working group. - Introduce regular student voice sessions. - Provide CPD for teachers on mathematical talk & reasoning (via PMC “Promoting Maths Talk”). pmc.oide.ie+1 - Audit current maths planning to check where vocabulary and reasoning are explicitly scaffolded. - Use PMC Toolkit supports (key language, suggestions for teaching and children’s learning) in teacher planning. NCCA+1 | - Survey shows baseline awareness of wellbeing among staff/students. - Increase in observed teacher use of mathematical vocabulary and reasoning in lessons. - Planning documents show inclusion of vocabulary & reasoning. - Student feedback: children report more opportunities to explain their thinking. |
| 2026-2027 | Embedding and Expanding Focus on resilience, connectedness, inclusion, wellbeing across whole school. | Playful Pedagogy & Cognitive Challenge Target: Incorporate more playful, investigative, problem solving and modelling tasks particularly in middle & senior classes. | Wellbeing: introduce programmes/projects promoting resilience, social-emotional learning, peer support; ensure belonging & inclusion. - Teachers share examples of good practice in wellbeing & kindness, respect etc. - Maths: CPD on modelling, problem solving, using real-life contexts; share sample tasks from PMC Toolkit. - Revisit planning and observation shows more frequent cognitively challenging tasks. - Use PLCs (Professional Learning Communities) to plan tasks together, share resources. | Increase in tasks that demand higher order thinking in maths (reasoning, problem-solving) in observations / work samples. - Students express stronger confidence with problem solving and modelling. - Wellbeing measures: improved connectedness, reduced behavioural referrals, better sense of safety / inclusion. - Teachers more confident in playful pedagogy across all class levels. |
| 2027-2028 | Sustaining & Deepening Wellbeing Focus on student agency, student leadership, awareness, mental health supports, staff wellbeing. | Assessment for Learning & Mastery Target: Use formative assessment strategies effectively, monitor progression, close gaps, ensure equity. | - Wellbeing: student leadership roles in wellbeing; peer mentoring; embed mental health / emotional regulation practices; staff wellbeing measures (workload, professional support). - Maths: CPD on formative assessment in maths; use of progression continua & PLCs to track progress; ensure support for students who are struggling; challenge for advanced learners. - Home-school links: parents informed about the new maths approach, mathematical language, reasoning etc. - Reflective practice: classroom observations, peer feedback. | - Data shows reduced variance across classes; narrowing gaps. - Formative assessments used regularly with student feedback. - Student leadership in wellbeing visible and effective. - Staff wellbeing feedback improved. - Sustained improvements in mathematical reasoning and modelling across levels. |

## Implementation Details

Stakeholders & Roles

- SSE / Wellbeing Lead(s)

- Maths Coordinator(s)

- All teaching staff

- Student Voice Committee

- Parents / Board of Management

Resources

- Use the PMC Toolkit (language, teaching suggestions, environment, home learning) to support maths targets. NCCA

- Wellbeing resources: PDST / Oide, NEPS guidelines, Catalogue of Wellbeing Resources for Primary Schools. gov.ie+1

- Use inspections insights (from Charting New Directions) to shape PD and resource allocation, especially around mathematical communication & playfulness. gov.ie+1

Monitoring & Evaluation

- Regular termly review of progress in both wellbeing and mathematics.

- Use mixed methods: surveys, work samples, lesson observations, student voice, teacher reflection.

- Mid-cycle review (end Year 2: Summer 2027) to assess what’s working; adjust targets/strategies.

Reporting & Sustainability

- Share results with school community: staff, students, parents, BOM.

- Identify practices to be embedded long-term.

- Ensure documentation (policies, planning templates) updated.